APPENDIX F - WORK PLAN

STRATEGIC GROWTH COUNCIL/Department of Conservation– Sustainable Communities Planning Grant Award

Grantee:   City of San Diego        Grant Number: 3014-624

Jurisdiction:  City of San Diego     Department: Planning

Project Title: Balboa Avenue Station Area Plan

| High Level Activities/Milestones (with Deliverables and Indicators) | Responsible Parties | Timetable in months (Start year: 2015) |
| --- | --- | --- |
| - Project Contracting - Finalize Scope of Work for Consultant Team - Consultant Procurement Process Deliverables: Scope of Work; Request for Proposal; Consultant Contract; Meeting Notes | City, SANDAG, CirculateSD, Consultant Team | Month One to Month Three |
| - Project Administration & Management - Bi-Monthly Coordination Meetings - Project Schedule & Management - Quarterly Invoices & Reports - Grant Close Out Deliverables: Meeting Notes; Project Schedule; Progress Reports; Invoices | City, SANDAG, CirculateSD, Consultant Team | Duration of the Plan – Thirty-six months Month Thirty-Four to Month Thirty-Six |
| - Community Outreach & Participation - Outreach & Participation Plan - Community Outreach Workshops - Community Planning Group Updates - Multi-modal Mobility Survey - Walk Audit - Online Communications Development Deliverables: Outreach & Participation Plan; Workshops, Notices, Summaries, Materials; Communtiy Planning Group Updates; Presentation Materials; Multi-modal Mobility Survey; Walk Audit; Online Materials and Useage Data | City, SANDAG, CirculateSD, Consultant Team | Duration of the Plan – Thirty-six months |
| - Existing Conditions Analysis, Opprtunities & Constraints - Environmental Reconnaissance - Land Use Assessment - Market Assessment - Multi-modal Mobility Assessment Deliverables: Existing Conditions technical memos, report; Maps | City, SANDAG, Consultant Team | Month Three to Month Seven |
| - Urban Design and Land Use Analysis - Opportunities and Constraints Mapping - Urban Design Vision - Land Use Scenarios - Multi-modal Land Use Scenario Evaluation - Preferred Land Use Deliverables: Opportunities and Constraints Mapping; Urban Design Visioning Report & Graphics; 2 Land Use Scenarios; Maps, GIS Data; Evaluation Matrix/Report; Preferred Land Use; Illustrations | City, SANDAG, Consultant Team | Month Seven to Month Eleven |
| - Economic Feasibility Analysis - Market Analysis - Financial Feasibility - Financing Strategies - Fiscal Impact Analyses Deliverables: Draft technical memos, reports; Pro-formas | City, Consultant Team | Month Eleven to Month Fourteen |
| - Multi-Modal Mobility Study - Future travel forecasting - Mobility Concept Development and Initial Vetting (multi-modal access to transit) - Future Conditions Analysis with Mobility Concept Plan - Transportation Impact Analysis as Needed Deliverables: Draft technical memos; Analysis Report; Mobility Recommendations, feasibility analysis, concept plan and drawings; Project list with detailed cost estimates. | City, SANDAG, Consultant Team | Month Fourteen to Month Seventeen |
| - Environmental Analysis - Prepare Technical Studies - Prepare of CEQA Document Screenchecks - Prepare Draft and Final CEQA Document Deliverables: Technical studies and anlaysis; Draft & Final Environmental Document | City, Consultant Team | Month Seventeen to Month Thirty-three |
| - Draft & Final Station Area Plan - Community Plan Amendments, Rezone, Facilities Financing Plan Amendments - Specific Plan - Implementation Plan Deliverables: Draft & Final Community Plan Amendment, Facilities Financing Plan, Zoning Map, Specific Plan, Implementation Plan | City, SANDAG, Consultant Team | Month Thirty-Two to Month Thirty-Six |